APPENDIX K:  Sample of a Proposed Call Timeline

| DATE | COMMENTS | TASK |
| --- | --- | --- |
| Year |  |  |
| 8-Nov | 1st meeting | Get to know each other, select officers. |
| 9-Nov | Meet with Bishop | Orientation |
| 15-Nov |  | Meet with Communication task force members. Set Timeline. Start review of Profile. |
| 22-Nov | Thanksgiving week | Complete MSP review. Solicit congregation for pastoral suggestions in bulletin 11/21, 11/29, 12/6. |
| 29-Nov |  | Select Interview Questions. |
| 6-Dec |  | Timeline and Questions complete. Practice interview. |
| 13-Dec |  | Get candidates' names from Bishop. Distribute candidate info. |
| 20-Dec | Christmas week | Initial discussion of candidates. Contact candidates and request copies of sermons? |
| 27-Dec |  | Holiday break? |
| Year |  |  |
| 3-Jan |  | Schedule initial interviews. |
| 10-Jan |  | Begin Interviews |
| 17-Jan |  | Continue interviews? |
| 24-Jan |  | Evaluate candidates. Background check. |
| 31-Jan |  | Schedule site visits. |
| 7-Feb |  | Visits |
| 14-Feb |  | Visits |
| 21-Feb |  | Face to Face Interviews. |
| 28-Feb |  | Evaluation |
| 7-Mar | Ash Wed. is March 9 | Evaluation |
| 14-Mar |  | Final Visit/Introduce to congregation. |
| 21-Mar |  | Recommend to Council. |
| 28-Mar |  | Congregational meeting. |
| 4-Apr |  | Issue call. |
| 11-Apr |  |  |
| 18-Apr |  |  |
| 25-Apr | Easter is April 24 |  |
| 2-May |  | Receive new pastor. |